## project WBS monitor
project: | WorkBreakdown Structure (WBS) monitor |  |  | remark | WBS id is reference to chapter in functional design (FD)
calculator: |  |  |  | remark | for FD: chapter are not chronological
date: | 2017-11-08 |  |  | do not | change the WBS id number for a task
WBS id | predecessor | task | requirement level (MoSCoW) | developer | Risc | duration, hr (plan) | duration, hr (do) | evaluation (check) | action (act)
1 |  | Speelveld | M | RBEZ |  | 20
2 |  | Tabcontrolls | M | RBEZ |  | 1
3 |  | Verplaatsbare boten | M | RBEZ/JLAV |  | 10
4 |  | C# Controlls | M | JLAV |  | 4
5 |  | Tabcontroll | M | JLAV |  | 1
6 |  | C# Geluiden | M | JLAV |  | 1
7 |  | Arduino controls | M | JLAV |  | 15
8 |  | Geschoten kogels | M | RBEZ |  | 1
9 |  | Switch bare speelvelden op basis van beurt (arduino) | M | RBEZ |  | 2
10 |  | Arduino scherm verschil tussen schiet pogingen en boot zichtbaar | M | RBEZ |  | 1
11 |  | Naam | S | JLAV |  | 1
12 |  | Ranglijst | S | RBEZ |  | 5
13 |  | arduino geluiden | S | JLAV |  | 4
14 |  | Multiplayer (internet) | C | RBEZ/JLAV
15 |  | Website (Ranglijst) | C | RBEZ |  | 5
16 |  | Startscherm | S | JLAV |  | 3
17 |  | Plaatjes | C | RBEZ/JLAV |  | 5
18
|  | total |  |  |  | 79 | 0

## MoSCoW
M | MUST | Describes a requirement that must be satisfied in the final solution for the solution to be considered a success.
S | SHOULD | Represents a high-priority item that should be included in the solution if it is possible. This is often a critical requirement but one which can be satisfied in other ways if strictly necessary.
C | COULD | Describes a requirement which is considered desirable but not necessary. This will be included if time and resources permit.
W | WON'T | Represents a requirement that stakeholders have agreed will not be implemented in a given release, but may be considered for the future. (note: occasionally the word "Would" is substituted for "Won't" to give a clearer understanding of this choice).

## version
datum | door | versieomschrijving
2015-10-09 | kadi | originele basisversie aangepast aan ideeën van Six Sigma